## TASK
task_code | status_code | wbs_id | task_name | task_type | target_drtn_hr_cnt
Activity ID | Activity Status | WBS Code | Activity Name | Activity Type | Original Duration(d)
A1010 | Not Started | TWR.GENERAL | Notice to Proceed | Start Milestone | 0
A1020 | Not Started | TWR.GENERAL | Mobilization & Site Setup | Task Dependent | 20
A1030 | Not Started | TWR.GENERAL | Project Management & Supervision | Level of Effort | 750
A1040 | Not Started | TWR.GENERAL | Structure Complete | Finish Milestone | 0
A1050 | Not Started | TWR.GENERAL | Practical Completion | Finish Milestone | 0
A1060 | Not Started | TWR.SUBSTRUCTU.EARTHWORKS | Bulk Excavation | Task Dependent | 60
A1070 | Not Started | TWR.SUBSTRUCTU.EARTHWORKS | Shoring - Secant Pile Wall | Task Dependent | 50
A1080 | Not Started | TWR.SUBSTRUCTU.EARTHWORKS | Dewatering | Task Dependent | 75
A1090 | Not Started | TWR.SUBSTRUCTU.PILING | Bored Piling Zone A | Task Dependent | 40
A1100 | Not Started | TWR.SUBSTRUCTU.PILING | Bored Piling Zone B | Task Dependent | 40
A1110 | Not Started | TWR.SUBSTRUCTU.FOUNDATION | Pile Caps Zone A | Task Dependent | 20
A1120 | Not Started | TWR.SUBSTRUCTU.FOUNDATION | Pile Caps Zone B | Task Dependent | 20
A1130 | Not Started | TWR.SUBSTRUCTU.FOUNDATION | Blinding Concrete - Zone A | Task Dependent | 5
A1140 | Not Started | TWR.SUBSTRUCTU.FOUNDATION | Blinding Concrete - Zone B | Task Dependent | 5
A1150 | Not Started | TWR.SUBSTRUCTU.FOUNDATION | Raft Waterproofing | Task Dependent | 15
A1160 | Not Started | TWR.SUBSTRUCTU.FOUNDATION | Raft Foundation - Zone A | Task Dependent | 25
A1170 | Not Started | TWR.SUBSTRUCTU.FOUNDATION | Raft Foundation - Zone B | Task Dependent | 25
A1180 | Not Started | TWR.SUBSTRUCTU.EARTHWORKS | Backfilling | Task Dependent | 20
A1190 | Not Started | TWR.SUPERSTRUC.B2 | B2 Zone A - Column Rebar | Task Dependent | 3
A1200 | Not Started | TWR.SUPERSTRUC.B2 | B2 Zone A - Column Formwork | Task Dependent | 3
A1210 | Not Started | TWR.SUPERSTRUC.B2 | B2 Zone A - Column Concrete | Task Dependent | 3
A1220 | Not Started | TWR.SUPERSTRUC.B2 | B2 Zone B - Column Rebar | Task Dependent | 3
A1230 | Not Started | TWR.SUPERSTRUC.B2 | B2 Zone B - Column Formwork | Task Dependent | 3
A1240 | Not Started | TWR.SUPERSTRUC.B2 | B2 Zone B - Column Concrete | Task Dependent | 3
A1250 | Not Started | TWR.SUPERSTRUC.B2 | B2 - Core Wall Rebar | Task Dependent | 4
A1260 | Not Started | TWR.SUPERSTRUC.B2 | B2 - Core Wall Formwork | Task Dependent | 4
A1270 | Not Started | TWR.SUPERSTRUC.B2 | B2 - Core Wall Concrete | Task Dependent | 4
A1280 | Not Started | TWR.SUPERSTRUC.B2 | B2 Zone A - Slab Formwork | Task Dependent | 5
A1290 | Not Started | TWR.SUPERSTRUC.B2 | B2 Zone A - Slab Rebar | Task Dependent | 5
A1300 | Not Started | TWR.SUPERSTRUC.B2 | B2 Zone A - Slab Concrete Pour | Task Dependent | 5
A1310 | Not Started | TWR.SUPERSTRUC.B2 | B2 Zone B - Slab Formwork | Task Dependent | 5
A1320 | Not Started | TWR.SUPERSTRUC.B2 | B2 Zone B - Slab Rebar | Task Dependent | 5
A1330 | Not Started | TWR.SUPERSTRUC.B2 | B2 Zone B - Slab Concrete Pour | Task Dependent | 5
A1340 | Not Started | TWR.SUPERSTRUC.B2 | B2 - Staircase Construction | Task Dependent | 5
A1350 | Not Started | TWR.SUPERSTRUC.B1 | B1 Zone A - Column Rebar | Task Dependent | 3
A1360 | Not Started | TWR.SUPERSTRUC.B1 | B1 Zone A - Column Formwork | Task Dependent | 3
A1370 | Not Started | TWR.SUPERSTRUC.B1 | B1 Zone A - Column Concrete | Task Dependent | 3
A1380 | Not Started | TWR.SUPERSTRUC.B1 | B1 Zone B - Column Rebar | Task Dependent | 3
A1390 | Not Started | TWR.SUPERSTRUC.B1 | B1 Zone B - Column Formwork | Task Dependent | 3
A1400 | Not Started | TWR.SUPERSTRUC.B1 | B1 Zone B - Column Concrete | Task Dependent | 3
A1410 | Not Started | TWR.SUPERSTRUC.B1 | B1 - Core Wall Rebar | Task Dependent | 4
A1420 | Not Started | TWR.SUPERSTRUC.B1 | B1 - Core Wall Formwork | Task Dependent | 4
A1430 | Not Started | TWR.SUPERSTRUC.B1 | B1 - Core Wall Concrete | Task Dependent | 4
A1440 | Not Started | TWR.SUPERSTRUC.B1 | B1 Zone A - Slab Formwork | Task Dependent | 5
A1450 | Not Started | TWR.SUPERSTRUC.B1 | B1 Zone A - Slab Rebar | Task Dependent | 5
A1460 | Not Started | TWR.SUPERSTRUC.B1 | B1 Zone A - Slab Concrete Pour | Task Dependent | 5
A1470 | Not Started | TWR.SUPERSTRUC.B1 | B1 Zone B - Slab Formwork | Task Dependent | 5
A1480 | Not Started | TWR.SUPERSTRUC.B1 | B1 Zone B - Slab Rebar | Task Dependent | 5
A1490 | Not Started | TWR.SUPERSTRUC.B1 | B1 Zone B - Slab Concrete Pour | Task Dependent | 5
A1500 | Not Started | TWR.SUPERSTRUC.B1 | B1 - Staircase Construction | Task Dependent | 5
A1510 | Not Started | TWR.SUPERSTRUC.GF | GF Zone A - Column Rebar | Task Dependent | 3
A1520 | Not Started | TWR.SUPERSTRUC.GF | GF Zone A - Column Formwork | Task Dependent | 3
A1530 | Not Started | TWR.SUPERSTRUC.GF | GF Zone A - Column Concrete | Task Dependent | 3
A1540 | Not Started | TWR.SUPERSTRUC.GF | GF Zone B - Column Rebar | Task Dependent | 3
A1550 | Not Started | TWR.SUPERSTRUC.GF | GF Zone B - Column Formwork | Task Dependent | 3
A1560 | Not Started | TWR.SUPERSTRUC.GF | GF Zone B - Column Concrete | Task Dependent | 3
A1570 | Not Started | TWR.SUPERSTRUC.GF | GF - Core Wall Rebar | Task Dependent | 4
A1580 | Not Started | TWR.SUPERSTRUC.GF | GF - Core Wall Formwork | Task Dependent | 4
A1590 | Not Started | TWR.SUPERSTRUC.GF | GF - Core Wall Concrete | Task Dependent | 4
A1600 | Not Started | TWR.SUPERSTRUC.GF | GF Zone A - Slab Formwork | Task Dependent | 5
A1610 | Not Started | TWR.SUPERSTRUC.GF | GF Zone A - Slab Rebar | Task Dependent | 5
A1620 | Not Started | TWR.SUPERSTRUC.GF | GF Zone A - Slab Concrete Pour | Task Dependent | 5
A1630 | Not Started | TWR.SUPERSTRUC.GF | GF Zone B - Slab Formwork | Task Dependent | 5
A1640 | Not Started | TWR.SUPERSTRUC.GF | GF Zone B - Slab Rebar | Task Dependent | 5
A1650 | Not Started | TWR.SUPERSTRUC.GF | GF Zone B - Slab Concrete Pour | Task Dependent | 5
A1660 | Not Started | TWR.SUPERSTRUC.GF | GF - Staircase Construction | Task Dependent | 5
A1670 | Not Started | TWR.SUPERSTRUC.L01 | L01 Zone A - Column Rebar | Task Dependent | 3
A1680 | Not Started | TWR.SUPERSTRUC.L01 | L01 Zone A - Column Formwork | Task Dependent | 3
A1690 | Not Started | TWR.SUPERSTRUC.L01 | L01 Zone A - Column Concrete | Task Dependent | 3
A1700 | Not Started | TWR.SUPERSTRUC.L01 | L01 Zone B - Column Rebar | Task Dependent | 3
A1710 | Not Started | TWR.SUPERSTRUC.L01 | L01 Zone B - Column Formwork | Task Dependent | 3
A1720 | Not Started | TWR.SUPERSTRUC.L01 | L01 Zone B - Column Concrete | Task Dependent | 3
A1730 | Not Started | TWR.SUPERSTRUC.L01 | L01 - Core Wall Rebar | Task Dependent | 4
A1740 | Not Started | TWR.SUPERSTRUC.L01 | L01 - Core Wall Formwork | Task Dependent | 4
A1750 | Not Started | TWR.SUPERSTRUC.L01 | L01 - Core Wall Concrete | Task Dependent | 4
A1760 | Not Started | TWR.SUPERSTRUC.L01 | L01 Zone A - Slab Formwork | Task Dependent | 5
A1770 | Not Started | TWR.SUPERSTRUC.L01 | L01 Zone A - Slab Rebar | Task Dependent | 5
A1780 | Not Started | TWR.SUPERSTRUC.L01 | L01 Zone A - Slab Concrete Pour | Task Dependent | 5
A1790 | Not Started | TWR.SUPERSTRUC.L01 | L01 Zone B - Slab Formwork | Task Dependent | 5
A1800 | Not Started | TWR.SUPERSTRUC.L01 | L01 Zone B - Slab Rebar | Task Dependent | 5
A1810 | Not Started | TWR.SUPERSTRUC.L01 | L01 Zone B - Slab Concrete Pour | Task Dependent | 5
A1820 | Not Started | TWR.SUPERSTRUC.L01 | L01 - Staircase Construction | Task Dependent | 5
A1830 | Not Started | TWR.SUPERSTRUC.L02 | L02 Zone A - Column Rebar | Task Dependent | 3
A1840 | Not Started | TWR.SUPERSTRUC.L02 | L02 Zone A - Column Formwork | Task Dependent | 3
A1850 | Not Started | TWR.SUPERSTRUC.L02 | L02 Zone A - Column Concrete | Task Dependent | 3
A1860 | Not Started | TWR.SUPERSTRUC.L02 | L02 Zone B - Column Rebar | Task Dependent | 3
A1870 | Not Started | TWR.SUPERSTRUC.L02 | L02 Zone B - Column Formwork | Task Dependent | 3
A1880 | Not Started | TWR.SUPERSTRUC.L02 | L02 Zone B - Column Concrete | Task Dependent | 3
A1890 | Not Started | TWR.SUPERSTRUC.L02 | L02 - Core Wall Rebar | Task Dependent | 4
A1900 | Not Started | TWR.SUPERSTRUC.L02 | L02 - Core Wall Formwork | Task Dependent | 4
A1910 | Not Started | TWR.SUPERSTRUC.L02 | L02 - Core Wall Concrete | Task Dependent | 4
A1920 | Not Started | TWR.SUPERSTRUC.L02 | L02 Zone A - Slab Formwork | Task Dependent | 5
A1930 | Not Started | TWR.SUPERSTRUC.L02 | L02 Zone A - Slab Rebar | Task Dependent | 5
A1940 | Not Started | TWR.SUPERSTRUC.L02 | L02 Zone A - Slab Concrete Pour | Task Dependent | 5
A1950 | Not Started | TWR.SUPERSTRUC.L02 | L02 Zone B - Slab Formwork | Task Dependent | 5
A1960 | Not Started | TWR.SUPERSTRUC.L02 | L02 Zone B - Slab Rebar | Task Dependent | 5
A1970 | Not Started | TWR.SUPERSTRUC.L02 | L02 Zone B - Slab Concrete Pour | Task Dependent | 5
A1980 | Not Started | TWR.SUPERSTRUC.L02 | L02 - Staircase Construction | Task Dependent | 5
A1990 | Not Started | TWR.SUPERSTRUC.L03 | L03 Zone A - Column Rebar | Task Dependent | 3
A2000 | Not Started | TWR.SUPERSTRUC.L03 | L03 Zone A - Column Formwork | Task Dependent | 3
A2010 | Not Started | TWR.SUPERSTRUC.L03 | L03 Zone A - Column Concrete | Task Dependent | 3
A2020 | Not Started | TWR.SUPERSTRUC.L03 | L03 Zone B - Column Rebar | Task Dependent | 3
A2030 | Not Started | TWR.SUPERSTRUC.L03 | L03 Zone B - Column Formwork | Task Dependent | 3
A2040 | Not Started | TWR.SUPERSTRUC.L03 | L03 Zone B - Column Concrete | Task Dependent | 3
A2050 | Not Started | TWR.SUPERSTRUC.L03 | L03 - Core Wall Rebar | Task Dependent | 4
A2060 | Not Started | TWR.SUPERSTRUC.L03 | L03 - Core Wall Formwork | Task Dependent | 4
A2070 | Not Started | TWR.SUPERSTRUC.L03 | L03 - Core Wall Concrete | Task Dependent | 4
A2080 | Not Started | TWR.SUPERSTRUC.L03 | L03 Zone A - Slab Formwork | Task Dependent | 5
A2090 | Not Started | TWR.SUPERSTRUC.L03 | L03 Zone A - Slab Rebar | Task Dependent | 5
A2100 | Not Started | TWR.SUPERSTRUC.L03 | L03 Zone A - Slab Concrete Pour | Task Dependent | 5
A2110 | Not Started | TWR.SUPERSTRUC.L03 | L03 Zone B - Slab Formwork | Task Dependent | 5
A2120 | Not Started | TWR.SUPERSTRUC.L03 | L03 Zone B - Slab Rebar | Task Dependent | 5
A2130 | Not Started | TWR.SUPERSTRUC.L03 | L03 Zone B - Slab Concrete Pour | Task Dependent | 5
A2140 | Not Started | TWR.SUPERSTRUC.L03 | L03 - Staircase Construction | Task Dependent | 5
A2150 | Not Started | TWR.SUPERSTRUC.L04 | L04 Zone A - Column Rebar | Task Dependent | 3
A2160 | Not Started | TWR.SUPERSTRUC.L04 | L04 Zone A - Column Formwork | Task Dependent | 3
A2170 | Not Started | TWR.SUPERSTRUC.L04 | L04 Zone A - Column Concrete | Task Dependent | 3
A2180 | Not Started | TWR.SUPERSTRUC.L04 | L04 Zone B - Column Rebar | Task Dependent | 3
A2190 | Not Started | TWR.SUPERSTRUC.L04 | L04 Zone B - Column Formwork | Task Dependent | 3
A2200 | Not Started | TWR.SUPERSTRUC.L04 | L04 Zone B - Column Concrete | Task Dependent | 3
A2210 | Not Started | TWR.SUPERSTRUC.L04 | L04 - Core Wall Rebar | Task Dependent | 4
A2220 | Not Started | TWR.SUPERSTRUC.L04 | L04 - Core Wall Formwork | Task Dependent | 4
A2230 | Not Started | TWR.SUPERSTRUC.L04 | L04 - Core Wall Concrete | Task Dependent | 4
A2240 | Not Started | TWR.SUPERSTRUC.L04 | L04 Zone A - Slab Formwork | Task Dependent | 5
A2250 | Not Started | TWR.SUPERSTRUC.L04 | L04 Zone A - Slab Rebar | Task Dependent | 5
A2260 | Not Started | TWR.SUPERSTRUC.L04 | L04 Zone A - Slab Concrete Pour | Task Dependent | 5
A2270 | Not Started | TWR.SUPERSTRUC.L04 | L04 Zone B - Slab Formwork | Task Dependent | 5
A2280 | Not Started | TWR.SUPERSTRUC.L04 | L04 Zone B - Slab Rebar | Task Dependent | 5
A2290 | Not Started | TWR.SUPERSTRUC.L04 | L04 Zone B - Slab Concrete Pour | Task Dependent | 5
A2300 | Not Started | TWR.SUPERSTRUC.L04 | L04 - Staircase Construction | Task Dependent | 5
A2310 | Not Started | TWR.SUPERSTRUC.L05 | L05 Zone A - Column Rebar | Task Dependent | 3
A2320 | Not Started | TWR.SUPERSTRUC.L05 | L05 Zone A - Column Formwork | Task Dependent | 3
A2330 | Not Started | TWR.SUPERSTRUC.L05 | L05 Zone A - Column Concrete | Task Dependent | 3
A2340 | Not Started | TWR.SUPERSTRUC.L05 | L05 Zone B - Column Rebar | Task Dependent | 3
A2350 | Not Started | TWR.SUPERSTRUC.L05 | L05 Zone B - Column Formwork | Task Dependent | 3
A2360 | Not Started | TWR.SUPERSTRUC.L05 | L05 Zone B - Column Concrete | Task Dependent | 3
A2370 | Not Started | TWR.SUPERSTRUC.L05 | L05 - Core Wall Rebar | Task Dependent | 4
A2380 | Not Started | TWR.SUPERSTRUC.L05 | L05 - Core Wall Formwork | Task Dependent | 4
A2390 | Not Started | TWR.SUPERSTRUC.L05 | L05 - Core Wall Concrete | Task Dependent | 4
A2400 | Not Started | TWR.SUPERSTRUC.L05 | L05 Zone A - Slab Formwork | Task Dependent | 5
A2410 | Not Started | TWR.SUPERSTRUC.L05 | L05 Zone A - Slab Rebar | Task Dependent | 5
A2420 | Not Started | TWR.SUPERSTRUC.L05 | L05 Zone A - Slab Concrete Pour | Task Dependent | 5
A2430 | Not Started | TWR.SUPERSTRUC.L05 | L05 Zone B - Slab Formwork | Task Dependent | 5
A2440 | Not Started | TWR.SUPERSTRUC.L05 | L05 Zone B - Slab Rebar | Task Dependent | 5
A2450 | Not Started | TWR.SUPERSTRUC.L05 | L05 Zone B - Slab Concrete Pour | Task Dependent | 5
A2460 | Not Started | TWR.SUPERSTRUC.L05 | L05 - Staircase Construction | Task Dependent | 5
A2470 | Not Started | TWR.SUPERSTRUC.L06 | L06 Zone A - Column Rebar | Task Dependent | 3
A2480 | Not Started | TWR.SUPERSTRUC.L06 | L06 Zone A - Column Formwork | Task Dependent | 3
A2490 | Not Started | TWR.SUPERSTRUC.L06 | L06 Zone A - Column Concrete | Task Dependent | 3
A2500 | Not Started | TWR.SUPERSTRUC.L06 | L06 Zone B - Column Rebar | Task Dependent | 3
A2510 | Not Started | TWR.SUPERSTRUC.L06 | L06 Zone B - Column Formwork | Task Dependent | 3
A2520 | Not Started | TWR.SUPERSTRUC.L06 | L06 Zone B - Column Concrete | Task Dependent | 3
A2530 | Not Started | TWR.SUPERSTRUC.L06 | L06 - Core Wall Rebar | Task Dependent | 4
A2540 | Not Started | TWR.SUPERSTRUC.L06 | L06 - Core Wall Formwork | Task Dependent | 4
A2550 | Not Started | TWR.SUPERSTRUC.L06 | L06 - Core Wall Concrete | Task Dependent | 4
A2560 | Not Started | TWR.SUPERSTRUC.L06 | L06 Zone A - Slab Formwork | Task Dependent | 5
A2570 | Not Started | TWR.SUPERSTRUC.L06 | L06 Zone A - Slab Rebar | Task Dependent | 5
A2580 | Not Started | TWR.SUPERSTRUC.L06 | L06 Zone A - Slab Concrete Pour | Task Dependent | 5
A2590 | Not Started | TWR.SUPERSTRUC.L06 | L06 Zone B - Slab Formwork | Task Dependent | 5
A2600 | Not Started | TWR.SUPERSTRUC.L06 | L06 Zone B - Slab Rebar | Task Dependent | 5
A2610 | Not Started | TWR.SUPERSTRUC.L06 | L06 Zone B - Slab Concrete Pour | Task Dependent | 5
A2620 | Not Started | TWR.SUPERSTRUC.L06 | L06 - Staircase Construction | Task Dependent | 5
A2630 | Not Started | TWR.SUPERSTRUC.L07 | L07 Zone A - Column Rebar | Task Dependent | 3
A2640 | Not Started | TWR.SUPERSTRUC.L07 | L07 Zone A - Column Formwork | Task Dependent | 3
A2650 | Not Started | TWR.SUPERSTRUC.L07 | L07 Zone A - Column Concrete | Task Dependent | 3
A2660 | Not Started | TWR.SUPERSTRUC.L07 | L07 Zone B - Column Rebar | Task Dependent | 3
A2670 | Not Started | TWR.SUPERSTRUC.L07 | L07 Zone B - Column Formwork | Task Dependent | 3
A2680 | Not Started | TWR.SUPERSTRUC.L07 | L07 Zone B - Column Concrete | Task Dependent | 3
A2690 | Not Started | TWR.SUPERSTRUC.L07 | L07 - Core Wall Rebar | Task Dependent | 4
A2700 | Not Started | TWR.SUPERSTRUC.L07 | L07 - Core Wall Formwork | Task Dependent | 4
A2710 | Not Started | TWR.SUPERSTRUC.L07 | L07 - Core Wall Concrete | Task Dependent | 4
A2720 | Not Started | TWR.SUPERSTRUC.L07 | L07 Zone A - Slab Formwork | Task Dependent | 5
A2730 | Not Started | TWR.SUPERSTRUC.L07 | L07 Zone A - Slab Rebar | Task Dependent | 5
A2740 | Not Started | TWR.SUPERSTRUC.L07 | L07 Zone A - Slab Concrete Pour | Task Dependent | 5
A2750 | Not Started | TWR.SUPERSTRUC.L07 | L07 Zone B - Slab Formwork | Task Dependent | 5
A2760 | Not Started | TWR.SUPERSTRUC.L07 | L07 Zone B - Slab Rebar | Task Dependent | 5
A2770 | Not Started | TWR.SUPERSTRUC.L07 | L07 Zone B - Slab Concrete Pour | Task Dependent | 5
A2780 | Not Started | TWR.SUPERSTRUC.L07 | L07 - Staircase Construction | Task Dependent | 5
A2790 | Not Started | TWR.SUPERSTRUC.L08 | L08 Zone A - Column Rebar | Task Dependent | 3
A2800 | Not Started | TWR.SUPERSTRUC.L08 | L08 Zone A - Column Formwork | Task Dependent | 3
A2810 | Not Started | TWR.SUPERSTRUC.L08 | L08 Zone A - Column Concrete | Task Dependent | 3
A2820 | Not Started | TWR.SUPERSTRUC.L08 | L08 Zone B - Column Rebar | Task Dependent | 3
A2830 | Not Started | TWR.SUPERSTRUC.L08 | L08 Zone B - Column Formwork | Task Dependent | 3
A2840 | Not Started | TWR.SUPERSTRUC.L08 | L08 Zone B - Column Concrete | Task Dependent | 3
A2850 | Not Started | TWR.SUPERSTRUC.L08 | L08 - Core Wall Rebar | Task Dependent | 4
A2860 | Not Started | TWR.SUPERSTRUC.L08 | L08 - Core Wall Formwork | Task Dependent | 4
A2870 | Not Started | TWR.SUPERSTRUC.L08 | L08 - Core Wall Concrete | Task Dependent | 4
A2880 | Not Started | TWR.SUPERSTRUC.L08 | L08 Zone A - Slab Formwork | Task Dependent | 5
A2890 | Not Started | TWR.SUPERSTRUC.L08 | L08 Zone A - Slab Rebar | Task Dependent | 5
A2900 | Not Started | TWR.SUPERSTRUC.L08 | L08 Zone A - Slab Concrete Pour | Task Dependent | 5
A2910 | Not Started | TWR.SUPERSTRUC.L08 | L08 Zone B - Slab Formwork | Task Dependent | 5
A2920 | Not Started | TWR.SUPERSTRUC.L08 | L08 Zone B - Slab Rebar | Task Dependent | 5
A2930 | Not Started | TWR.SUPERSTRUC.L08 | L08 Zone B - Slab Concrete Pour | Task Dependent | 5
A2940 | Not Started | TWR.SUPERSTRUC.L08 | L08 - Staircase Construction | Task Dependent | 5
A2950 | Not Started | TWR.SUPERSTRUC.L09 | L09 Zone A - Column Rebar | Task Dependent | 3
A2960 | Not Started | TWR.SUPERSTRUC.L09 | L09 Zone A - Column Formwork | Task Dependent | 3
A2970 | Not Started | TWR.SUPERSTRUC.L09 | L09 Zone A - Column Concrete | Task Dependent | 3
A2980 | Not Started | TWR.SUPERSTRUC.L09 | L09 Zone B - Column Rebar | Task Dependent | 3
A2990 | Not Started | TWR.SUPERSTRUC.L09 | L09 Zone B - Column Formwork | Task Dependent | 3
A3000 | Not Started | TWR.SUPERSTRUC.L09 | L09 Zone B - Column Concrete | Task Dependent | 3
A3010 | Not Started | TWR.SUPERSTRUC.L09 | L09 - Core Wall Rebar | Task Dependent | 4
A3020 | Not Started | TWR.SUPERSTRUC.L09 | L09 - Core Wall Formwork | Task Dependent | 4
A3030 | Not Started | TWR.SUPERSTRUC.L09 | L09 - Core Wall Concrete | Task Dependent | 4
A3040 | Not Started | TWR.SUPERSTRUC.L09 | L09 Zone A - Slab Formwork | Task Dependent | 5
A3050 | Not Started | TWR.SUPERSTRUC.L09 | L09 Zone A - Slab Rebar | Task Dependent | 5
A3060 | Not Started | TWR.SUPERSTRUC.L09 | L09 Zone A - Slab Concrete Pour | Task Dependent | 5
A3070 | Not Started | TWR.SUPERSTRUC.L09 | L09 Zone B - Slab Formwork | Task Dependent | 5
A3080 | Not Started | TWR.SUPERSTRUC.L09 | L09 Zone B - Slab Rebar | Task Dependent | 5
A3090 | Not Started | TWR.SUPERSTRUC.L09 | L09 Zone B - Slab Concrete Pour | Task Dependent | 5
A3100 | Not Started | TWR.SUPERSTRUC.L09 | L09 - Staircase Construction | Task Dependent | 5
A3110 | Not Started | TWR.SUPERSTRUC.L10 | L10 Zone A - Column Rebar | Task Dependent | 3
A3120 | Not Started | TWR.SUPERSTRUC.L10 | L10 Zone A - Column Formwork | Task Dependent | 3
A3130 | Not Started | TWR.SUPERSTRUC.L10 | L10 Zone A - Column Concrete | Task Dependent | 3
A3140 | Not Started | TWR.SUPERSTRUC.L10 | L10 Zone B - Column Rebar | Task Dependent | 3
A3150 | Not Started | TWR.SUPERSTRUC.L10 | L10 Zone B - Column Formwork | Task Dependent | 3
A3160 | Not Started | TWR.SUPERSTRUC.L10 | L10 Zone B - Column Concrete | Task Dependent | 3
A3170 | Not Started | TWR.SUPERSTRUC.L10 | L10 - Core Wall Rebar | Task Dependent | 4
A3180 | Not Started | TWR.SUPERSTRUC.L10 | L10 - Core Wall Formwork | Task Dependent | 4
A3190 | Not Started | TWR.SUPERSTRUC.L10 | L10 - Core Wall Concrete | Task Dependent | 4
A3200 | Not Started | TWR.SUPERSTRUC.L10 | L10 Zone A - Slab Formwork | Task Dependent | 5
A3210 | Not Started | TWR.SUPERSTRUC.L10 | L10 Zone A - Slab Rebar | Task Dependent | 5
A3220 | Not Started | TWR.SUPERSTRUC.L10 | L10 Zone A - Slab Concrete Pour | Task Dependent | 5
A3230 | Not Started | TWR.SUPERSTRUC.L10 | L10 Zone B - Slab Formwork | Task Dependent | 5
A3240 | Not Started | TWR.SUPERSTRUC.L10 | L10 Zone B - Slab Rebar | Task Dependent | 5
A3250 | Not Started | TWR.SUPERSTRUC.L10 | L10 Zone B - Slab Concrete Pour | Task Dependent | 5
A3260 | Not Started | TWR.SUPERSTRUC.L10 | L10 - Staircase Construction | Task Dependent | 5
A3270 | Not Started | TWR.SUPERSTRUC.L11 | L11 Zone A - Column Rebar | Task Dependent | 3
A3280 | Not Started | TWR.SUPERSTRUC.L11 | L11 Zone A - Column Formwork | Task Dependent | 3
A3290 | Not Started | TWR.SUPERSTRUC.L11 | L11 Zone A - Column Concrete | Task Dependent | 3
A3300 | Not Started | TWR.SUPERSTRUC.L11 | L11 Zone B - Column Rebar | Task Dependent | 3
A3310 | Not Started | TWR.SUPERSTRUC.L11 | L11 Zone B - Column Formwork | Task Dependent | 3
A3320 | Not Started | TWR.SUPERSTRUC.L11 | L11 Zone B - Column Concrete | Task Dependent | 3
A3330 | Not Started | TWR.SUPERSTRUC.L11 | L11 - Core Wall Rebar | Task Dependent | 4
A3340 | Not Started | TWR.SUPERSTRUC.L11 | L11 - Core Wall Formwork | Task Dependent | 4
A3350 | Not Started | TWR.SUPERSTRUC.L11 | L11 - Core Wall Concrete | Task Dependent | 4
A3360 | Not Started | TWR.SUPERSTRUC.L11 | L11 Zone A - Slab Formwork | Task Dependent | 5
A3370 | Not Started | TWR.SUPERSTRUC.L11 | L11 Zone A - Slab Rebar | Task Dependent | 5
A3380 | Not Started | TWR.SUPERSTRUC.L11 | L11 Zone A - Slab Concrete Pour | Task Dependent | 5
A3390 | Not Started | TWR.SUPERSTRUC.L11 | L11 Zone B - Slab Formwork | Task Dependent | 5
A3400 | Not Started | TWR.SUPERSTRUC.L11 | L11 Zone B - Slab Rebar | Task Dependent | 5
A3410 | Not Started | TWR.SUPERSTRUC.L11 | L11 Zone B - Slab Concrete Pour | Task Dependent | 5
A3420 | Not Started | TWR.SUPERSTRUC.L11 | L11 - Staircase Construction | Task Dependent | 5
A3430 | Not Started | TWR.SUPERSTRUC.L12 | L12 Zone A - Column Rebar | Task Dependent | 3
A3440 | Not Started | TWR.SUPERSTRUC.L12 | L12 Zone A - Column Formwork | Task Dependent | 3
A3450 | Not Started | TWR.SUPERSTRUC.L12 | L12 Zone A - Column Concrete | Task Dependent | 3
A3460 | Not Started | TWR.SUPERSTRUC.L12 | L12 Zone B - Column Rebar | Task Dependent | 3
A3470 | Not Started | TWR.SUPERSTRUC.L12 | L12 Zone B - Column Formwork | Task Dependent | 3
A3480 | Not Started | TWR.SUPERSTRUC.L12 | L12 Zone B - Column Concrete | Task Dependent | 3
A3490 | Not Started | TWR.SUPERSTRUC.L12 | L12 - Core Wall Rebar | Task Dependent | 4
A3500 | Not Started | TWR.SUPERSTRUC.L12 | L12 - Core Wall Formwork | Task Dependent | 4
A3510 | Not Started | TWR.SUPERSTRUC.L12 | L12 - Core Wall Concrete | Task Dependent | 4
A3520 | Not Started | TWR.SUPERSTRUC.L12 | L12 Zone A - Slab Formwork | Task Dependent | 5
A3530 | Not Started | TWR.SUPERSTRUC.L12 | L12 Zone A - Slab Rebar | Task Dependent | 5
A3540 | Not Started | TWR.SUPERSTRUC.L12 | L12 Zone A - Slab Concrete Pour | Task Dependent | 5
A3550 | Not Started | TWR.SUPERSTRUC.L12 | L12 Zone B - Slab Formwork | Task Dependent | 5
A3560 | Not Started | TWR.SUPERSTRUC.L12 | L12 Zone B - Slab Rebar | Task Dependent | 5
A3570 | Not Started | TWR.SUPERSTRUC.L12 | L12 Zone B - Slab Concrete Pour | Task Dependent | 5
A3580 | Not Started | TWR.SUPERSTRUC.L12 | L12 - Staircase Construction | Task Dependent | 5
A3590 | Not Started | TWR.SUPERSTRUC.L13 | L13 Zone A - Column Rebar | Task Dependent | 3
A3600 | Not Started | TWR.SUPERSTRUC.L13 | L13 Zone A - Column Formwork | Task Dependent | 3
A3610 | Not Started | TWR.SUPERSTRUC.L13 | L13 Zone A - Column Concrete | Task Dependent | 3
A3620 | Not Started | TWR.SUPERSTRUC.L13 | L13 Zone B - Column Rebar | Task Dependent | 3
A3630 | Not Started | TWR.SUPERSTRUC.L13 | L13 Zone B - Column Formwork | Task Dependent | 3
A3640 | Not Started | TWR.SUPERSTRUC.L13 | L13 Zone B - Column Concrete | Task Dependent | 3
A3650 | Not Started | TWR.SUPERSTRUC.L13 | L13 - Core Wall Rebar | Task Dependent | 4
A3660 | Not Started | TWR.SUPERSTRUC.L13 | L13 - Core Wall Formwork | Task Dependent | 4
A3670 | Not Started | TWR.SUPERSTRUC.L13 | L13 - Core Wall Concrete | Task Dependent | 4
A3680 | Not Started | TWR.SUPERSTRUC.L13 | L13 Zone A - Slab Formwork | Task Dependent | 5
A3690 | Not Started | TWR.SUPERSTRUC.L13 | L13 Zone A - Slab Rebar | Task Dependent | 5
A3700 | Not Started | TWR.SUPERSTRUC.L13 | L13 Zone A - Slab Concrete Pour | Task Dependent | 5
A3710 | Not Started | TWR.SUPERSTRUC.L13 | L13 Zone B - Slab Formwork | Task Dependent | 5
A3720 | Not Started | TWR.SUPERSTRUC.L13 | L13 Zone B - Slab Rebar | Task Dependent | 5
A3730 | Not Started | TWR.SUPERSTRUC.L13 | L13 Zone B - Slab Concrete Pour | Task Dependent | 5
A3740 | Not Started | TWR.SUPERSTRUC.L13 | L13 - Staircase Construction | Task Dependent | 5
A3750 | Not Started | TWR.SUPERSTRUC.L14 | L14 Zone A - Column Rebar | Task Dependent | 3
A3760 | Not Started | TWR.SUPERSTRUC.L14 | L14 Zone A - Column Formwork | Task Dependent | 3
A3770 | Not Started | TWR.SUPERSTRUC.L14 | L14 Zone A - Column Concrete | Task Dependent | 3
A3780 | Not Started | TWR.SUPERSTRUC.L14 | L14 Zone B - Column Rebar | Task Dependent | 3
A3790 | Not Started | TWR.SUPERSTRUC.L14 | L14 Zone B - Column Formwork | Task Dependent | 3
A3800 | Not Started | TWR.SUPERSTRUC.L14 | L14 Zone B - Column Concrete | Task Dependent | 3
A3810 | Not Started | TWR.SUPERSTRUC.L14 | L14 - Core Wall Rebar | Task Dependent | 4
A3820 | Not Started | TWR.SUPERSTRUC.L14 | L14 - Core Wall Formwork | Task Dependent | 4
A3830 | Not Started | TWR.SUPERSTRUC.L14 | L14 - Core Wall Concrete | Task Dependent | 4
A3840 | Not Started | TWR.SUPERSTRUC.L14 | L14 Zone A - Slab Formwork | Task Dependent | 5
A3850 | Not Started | TWR.SUPERSTRUC.L14 | L14 Zone A - Slab Rebar | Task Dependent | 5
A3860 | Not Started | TWR.SUPERSTRUC.L14 | L14 Zone A - Slab Concrete Pour | Task Dependent | 5
A3870 | Not Started | TWR.SUPERSTRUC.L14 | L14 Zone B - Slab Formwork | Task Dependent | 5
A3880 | Not Started | TWR.SUPERSTRUC.L14 | L14 Zone B - Slab Rebar | Task Dependent | 5
A3890 | Not Started | TWR.SUPERSTRUC.L14 | L14 Zone B - Slab Concrete Pour | Task Dependent | 5
A3900 | Not Started | TWR.SUPERSTRUC.L14 | L14 - Staircase Construction | Task Dependent | 5
A3910 | Not Started | TWR.SUPERSTRUC.L15 | L15 Zone A - Column Rebar | Task Dependent | 3
A3920 | Not Started | TWR.SUPERSTRUC.L15 | L15 Zone A - Column Formwork | Task Dependent | 3
A3930 | Not Started | TWR.SUPERSTRUC.L15 | L15 Zone A - Column Concrete | Task Dependent | 3
A3940 | Not Started | TWR.SUPERSTRUC.L15 | L15 Zone B - Column Rebar | Task Dependent | 3
A3950 | Not Started | TWR.SUPERSTRUC.L15 | L15 Zone B - Column Formwork | Task Dependent | 3
A3960 | Not Started | TWR.SUPERSTRUC.L15 | L15 Zone B - Column Concrete | Task Dependent | 3
A3970 | Not Started | TWR.SUPERSTRUC.L15 | L15 - Core Wall Rebar | Task Dependent | 4
A3980 | Not Started | TWR.SUPERSTRUC.L15 | L15 - Core Wall Formwork | Task Dependent | 4
A3990 | Not Started | TWR.SUPERSTRUC.L15 | L15 - Core Wall Concrete | Task Dependent | 4
A4000 | Not Started | TWR.SUPERSTRUC.L15 | L15 Zone A - Slab Formwork | Task Dependent | 5
A4010 | Not Started | TWR.SUPERSTRUC.L15 | L15 Zone A - Slab Rebar | Task Dependent | 5
A4020 | Not Started | TWR.SUPERSTRUC.L15 | L15 Zone A - Slab Concrete Pour | Task Dependent | 5
A4030 | Not Started | TWR.SUPERSTRUC.L15 | L15 Zone B - Slab Formwork | Task Dependent | 5
A4040 | Not Started | TWR.SUPERSTRUC.L15 | L15 Zone B - Slab Rebar | Task Dependent | 5
A4050 | Not Started | TWR.SUPERSTRUC.L15 | L15 Zone B - Slab Concrete Pour | Task Dependent | 5
A4060 | Not Started | TWR.SUPERSTRUC.L15 | L15 - Staircase Construction | Task Dependent | 5
A4070 | Not Started | TWR.SUPERSTRUC.L16 | L16 Zone A - Column Rebar | Task Dependent | 3
A4080 | Not Started | TWR.SUPERSTRUC.L16 | L16 Zone A - Column Formwork | Task Dependent | 3
A4090 | Not Started | TWR.SUPERSTRUC.L16 | L16 Zone A - Column Concrete | Task Dependent | 3
A4100 | Not Started | TWR.SUPERSTRUC.L16 | L16 Zone B - Column Rebar | Task Dependent | 3
A4110 | Not Started | TWR.SUPERSTRUC.L16 | L16 Zone B - Column Formwork | Task Dependent | 3
A4120 | Not Started | TWR.SUPERSTRUC.L16 | L16 Zone B - Column Concrete | Task Dependent | 3
A4130 | Not Started | TWR.SUPERSTRUC.L16 | L16 - Core Wall Rebar | Task Dependent | 4
A4140 | Not Started | TWR.SUPERSTRUC.L16 | L16 - Core Wall Formwork | Task Dependent | 4
A4150 | Not Started | TWR.SUPERSTRUC.L16 | L16 - Core Wall Concrete | Task Dependent | 4
A4160 | Not Started | TWR.SUPERSTRUC.L16 | L16 Zone A - Slab Formwork | Task Dependent | 5
A4170 | Not Started | TWR.SUPERSTRUC.L16 | L16 Zone A - Slab Rebar | Task Dependent | 5
A4180 | Not Started | TWR.SUPERSTRUC.L16 | L16 Zone A - Slab Concrete Pour | Task Dependent | 5
A4190 | Not Started | TWR.SUPERSTRUC.L16 | L16 Zone B - Slab Formwork | Task Dependent | 5
A4200 | Not Started | TWR.SUPERSTRUC.L16 | L16 Zone B - Slab Rebar | Task Dependent | 5
A4210 | Not Started | TWR.SUPERSTRUC.L16 | L16 Zone B - Slab Concrete Pour | Task Dependent | 5
A4220 | Not Started | TWR.SUPERSTRUC.L16 | L16 - Staircase Construction | Task Dependent | 5
A4230 | Not Started | TWR.SUPERSTRUC.L17 | L17 Zone A - Column Rebar | Task Dependent | 3
A4240 | Not Started | TWR.SUPERSTRUC.L17 | L17 Zone A - Column Formwork | Task Dependent | 3
A4250 | Not Started | TWR.SUPERSTRUC.L17 | L17 Zone A - Column Concrete | Task Dependent | 3
A4260 | Not Started | TWR.SUPERSTRUC.L17 | L17 Zone B - Column Rebar | Task Dependent | 3
A4270 | Not Started | TWR.SUPERSTRUC.L17 | L17 Zone B - Column Formwork | Task Dependent | 3
A4280 | Not Started | TWR.SUPERSTRUC.L17 | L17 Zone B - Column Concrete | Task Dependent | 3
A4290 | Not Started | TWR.SUPERSTRUC.L17 | L17 - Core Wall Rebar | Task Dependent | 4
A4300 | Not Started | TWR.SUPERSTRUC.L17 | L17 - Core Wall Formwork | Task Dependent | 4
A4310 | Not Started | TWR.SUPERSTRUC.L17 | L17 - Core Wall Concrete | Task Dependent | 4
A4320 | Not Started | TWR.SUPERSTRUC.L17 | L17 Zone A - Slab Formwork | Task Dependent | 5
A4330 | Not Started | TWR.SUPERSTRUC.L17 | L17 Zone A - Slab Rebar | Task Dependent | 5
A4340 | Not Started | TWR.SUPERSTRUC.L17 | L17 Zone A - Slab Concrete Pour | Task Dependent | 5
A4350 | Not Started | TWR.SUPERSTRUC.L17 | L17 Zone B - Slab Formwork | Task Dependent | 5
A4360 | Not Started | TWR.SUPERSTRUC.L17 | L17 Zone B - Slab Rebar | Task Dependent | 5
A4370 | Not Started | TWR.SUPERSTRUC.L17 | L17 Zone B - Slab Concrete Pour | Task Dependent | 5
A4380 | Not Started | TWR.SUPERSTRUC.L17 | L17 - Staircase Construction | Task Dependent | 5
A4390 | Not Started | TWR.SUPERSTRUC.RF | RF Zone A - Column Rebar | Task Dependent | 3
A4400 | Not Started | TWR.SUPERSTRUC.RF | RF Zone A - Column Formwork | Task Dependent | 3
A4410 | Not Started | TWR.SUPERSTRUC.RF | RF Zone A - Column Concrete | Task Dependent | 3
A4420 | Not Started | TWR.SUPERSTRUC.RF | RF Zone B - Column Rebar | Task Dependent | 3
A4430 | Not Started | TWR.SUPERSTRUC.RF | RF Zone B - Column Formwork | Task Dependent | 3
A4440 | Not Started | TWR.SUPERSTRUC.RF | RF Zone B - Column Concrete | Task Dependent | 3
A4450 | Not Started | TWR.SUPERSTRUC.RF | RF - Core Wall Rebar | Task Dependent | 4
A4460 | Not Started | TWR.SUPERSTRUC.RF | RF - Core Wall Formwork | Task Dependent | 4
A4470 | Not Started | TWR.SUPERSTRUC.RF | RF - Core Wall Concrete | Task Dependent | 4
A4480 | Not Started | TWR.SUPERSTRUC.RF | RF Zone A - Slab Formwork | Task Dependent | 5
A4490 | Not Started | TWR.SUPERSTRUC.RF | RF Zone A - Slab Rebar | Task Dependent | 5
A4500 | Not Started | TWR.SUPERSTRUC.RF | RF Zone A - Slab Concrete Pour | Task Dependent | 5
A4510 | Not Started | TWR.SUPERSTRUC.RF | RF Zone B - Slab Formwork | Task Dependent | 5
A4520 | Not Started | TWR.SUPERSTRUC.RF | RF Zone B - Slab Rebar | Task Dependent | 5
A4530 | Not Started | TWR.SUPERSTRUC.RF | RF Zone B - Slab Concrete Pour | Task Dependent | 5
A4540 | Not Started | TWR.SUPERSTRUC.RF | RF - Staircase Construction | Task Dependent | 5
A4550 | Not Started | TWR.FINISHES.GROUNDFLO | Blockwork - Ground Floor | Task Dependent | 10
A4560 | Not Started | TWR.FINISHES.GROUNDFLO | Electrical First Fix - Ground Floor | Task Dependent | 10
A4570 | Not Started | TWR.FINISHES.GROUNDFLO | Plumbing First Fix - Ground Floor | Task Dependent | 10
A4580 | Not Started | TWR.FINISHES.GROUNDFLO | HVAC Ductwork & FCU Installation - Ground Floor | Task Dependent | 10
A4590 | Not Started | TWR.FINISHES.GROUNDFLO | Fire Fighting Sprinkler Piping - Ground Floor | Task Dependent | 10
A4600 | Not Started | TWR.FINISHES.GROUNDFLO | Fire Alarm & ELV Containment - Ground Floor | Task Dependent | 10
A4610 | Not Started | TWR.FINISHES.GROUNDFLO | Internal Plaster - Ground Floor | Task Dependent | 10
A4620 | Not Started | TWR.FINISHES.GROUNDFLO | Floor Screed - Ground Floor | Task Dependent | 10
A4630 | Not Started | TWR.FINISHES.GROUNDFLO | Wet Area Waterproofing - Ground Floor | Task Dependent | 10
A4640 | Not Started | TWR.FINISHES.GROUNDFLO | False Ceiling - Ground Floor | Task Dependent | 10
A4650 | Not Started | TWR.FINISHES.GROUNDFLO | Floor & Wall Tiling - Ground Floor | Task Dependent | 10
A4660 | Not Started | TWR.FINISHES.GROUNDFLO | Painting - Ground Floor | Task Dependent | 10
A4670 | Not Started | TWR.FINISHES.GROUNDFLO | Doors & Ironmongery - Ground Floor | Task Dependent | 10
A4680 | Not Started | TWR.FINISHES.GROUNDFLO | Kitchen & Wardrobe Joinery - Ground Floor | Task Dependent | 10
A4690 | Not Started | TWR.FINISHES.GROUNDFLO | MEP Second Fix & Fixtures - Ground Floor | Task Dependent | 10
A4700 | Not Started | TWR.FINISHES.GROUNDFLO | Final Cleaning & Snagging - Ground Floor | Task Dependent | 10
A4710 | Not Started | TWR.FINISHES.LEVEL01 | Blockwork - Level 01 | Task Dependent | 10
A4720 | Not Started | TWR.FINISHES.LEVEL01 | Electrical First Fix - Level 01 | Task Dependent | 10
A4730 | Not Started | TWR.FINISHES.LEVEL01 | Plumbing First Fix - Level 01 | Task Dependent | 10
A4740 | Not Started | TWR.FINISHES.LEVEL01 | HVAC Ductwork & FCU Installation - Level 01 | Task Dependent | 10
A4750 | Not Started | TWR.FINISHES.LEVEL01 | Fire Fighting Sprinkler Piping - Level 01 | Task Dependent | 10
A4760 | Not Started | TWR.FINISHES.LEVEL01 | Fire Alarm & ELV Containment - Level 01 | Task Dependent | 10
A4770 | Not Started | TWR.FINISHES.LEVEL01 | Internal Plaster - Level 01 | Task Dependent | 10
A4780 | Not Started | TWR.FINISHES.LEVEL01 | Floor Screed - Level 01 | Task Dependent | 10
A4790 | Not Started | TWR.FINISHES.LEVEL01 | Wet Area Waterproofing - Level 01 | Task Dependent | 10
A4800 | Not Started | TWR.FINISHES.LEVEL01 | False Ceiling - Level 01 | Task Dependent | 10
A4810 | Not Started | TWR.FINISHES.LEVEL01 | Floor & Wall Tiling - Level 01 | Task Dependent | 10
A4820 | Not Started | TWR.FINISHES.LEVEL01 | Painting - Level 01 | Task Dependent | 10
A4830 | Not Started | TWR.FINISHES.LEVEL01 | Doors & Ironmongery - Level 01 | Task Dependent | 10
A4840 | Not Started | TWR.FINISHES.LEVEL01 | Kitchen & Wardrobe Joinery - Level 01 | Task Dependent | 10
A4850 | Not Started | TWR.FINISHES.LEVEL01 | MEP Second Fix & Fixtures - Level 01 | Task Dependent | 10
A4860 | Not Started | TWR.FINISHES.LEVEL01 | Final Cleaning & Snagging - Level 01 | Task Dependent | 10
A4870 | Not Started | TWR.FINISHES.LEVEL02 | Blockwork - Level 02 | Task Dependent | 10
A4880 | Not Started | TWR.FINISHES.LEVEL02 | Electrical First Fix - Level 02 | Task Dependent | 10
A4890 | Not Started | TWR.FINISHES.LEVEL02 | Plumbing First Fix - Level 02 | Task Dependent | 10
A4900 | Not Started | TWR.FINISHES.LEVEL02 | HVAC Ductwork & FCU Installation - Level 02 | Task Dependent | 10
A4910 | Not Started | TWR.FINISHES.LEVEL02 | Fire Fighting Sprinkler Piping - Level 02 | Task Dependent | 10
A4920 | Not Started | TWR.FINISHES.LEVEL02 | Fire Alarm & ELV Containment - Level 02 | Task Dependent | 10
A4930 | Not Started | TWR.FINISHES.LEVEL02 | Internal Plaster - Level 02 | Task Dependent | 10
A4940 | Not Started | TWR.FINISHES.LEVEL02 | Floor Screed - Level 02 | Task Dependent | 10
A4950 | Not Started | TWR.FINISHES.LEVEL02 | Wet Area Waterproofing - Level 02 | Task Dependent | 10
A4960 | Not Started | TWR.FINISHES.LEVEL02 | False Ceiling - Level 02 | Task Dependent | 10
A4970 | Not Started | TWR.FINISHES.LEVEL02 | Floor & Wall Tiling - Level 02 | Task Dependent | 10
A4980 | Not Started | TWR.FINISHES.LEVEL02 | Painting - Level 02 | Task Dependent | 10
A4990 | Not Started | TWR.FINISHES.LEVEL02 | Doors & Ironmongery - Level 02 | Task Dependent | 10
A5000 | Not Started | TWR.FINISHES.LEVEL02 | Kitchen & Wardrobe Joinery - Level 02 | Task Dependent | 10
A5010 | Not Started | TWR.FINISHES.LEVEL02 | MEP Second Fix & Fixtures - Level 02 | Task Dependent | 10
A5020 | Not Started | TWR.FINISHES.LEVEL02 | Final Cleaning & Snagging - Level 02 | Task Dependent | 10
A5030 | Not Started | TWR.FINISHES.LEVEL03 | Blockwork - Level 03 | Task Dependent | 10
A5040 | Not Started | TWR.FINISHES.LEVEL03 | Electrical First Fix - Level 03 | Task Dependent | 10
A5050 | Not Started | TWR.FINISHES.LEVEL03 | Plumbing First Fix - Level 03 | Task Dependent | 10
A5060 | Not Started | TWR.FINISHES.LEVEL03 | HVAC Ductwork & FCU Installation - Level 03 | Task Dependent | 10
A5070 | Not Started | TWR.FINISHES.LEVEL03 | Fire Fighting Sprinkler Piping - Level 03 | Task Dependent | 10
A5080 | Not Started | TWR.FINISHES.LEVEL03 | Fire Alarm & ELV Containment - Level 03 | Task Dependent | 10
A5090 | Not Started | TWR.FINISHES.LEVEL03 | Internal Plaster - Level 03 | Task Dependent | 10
A5100 | Not Started | TWR.FINISHES.LEVEL03 | Floor Screed - Level 03 | Task Dependent | 10
A5110 | Not Started | TWR.FINISHES.LEVEL03 | Wet Area Waterproofing - Level 03 | Task Dependent | 10
A5120 | Not Started | TWR.FINISHES.LEVEL03 | False Ceiling - Level 03 | Task Dependent | 10
A5130 | Not Started | TWR.FINISHES.LEVEL03 | Floor & Wall Tiling - Level 03 | Task Dependent | 10
A5140 | Not Started | TWR.FINISHES.LEVEL03 | Painting - Level 03 | Task Dependent | 10
A5150 | Not Started | TWR.FINISHES.LEVEL03 | Doors & Ironmongery - Level 03 | Task Dependent | 10
A5160 | Not Started | TWR.FINISHES.LEVEL03 | Kitchen & Wardrobe Joinery - Level 03 | Task Dependent | 10
A5170 | Not Started | TWR.FINISHES.LEVEL03 | MEP Second Fix & Fixtures - Level 03 | Task Dependent | 10
A5180 | Not Started | TWR.FINISHES.LEVEL03 | Final Cleaning & Snagging - Level 03 | Task Dependent | 10
A5190 | Not Started | TWR.FINISHES.LEVEL04 | Blockwork - Level 04 | Task Dependent | 10
A5200 | Not Started | TWR.FINISHES.LEVEL04 | Electrical First Fix - Level 04 | Task Dependent | 10
A5210 | Not Started | TWR.FINISHES.LEVEL04 | Plumbing First Fix - Level 04 | Task Dependent | 10
A5220 | Not Started | TWR.FINISHES.LEVEL04 | HVAC Ductwork & FCU Installation - Level 04 | Task Dependent | 10
A5230 | Not Started | TWR.FINISHES.LEVEL04 | Fire Fighting Sprinkler Piping - Level 04 | Task Dependent | 10
A5240 | Not Started | TWR.FINISHES.LEVEL04 | Fire Alarm & ELV Containment - Level 04 | Task Dependent | 10
A5250 | Not Started | TWR.FINISHES.LEVEL04 | Internal Plaster - Level 04 | Task Dependent | 10
A5260 | Not Started | TWR.FINISHES.LEVEL04 | Floor Screed - Level 04 | Task Dependent | 10
A5270 | Not Started | TWR.FINISHES.LEVEL04 | Wet Area Waterproofing - Level 04 | Task Dependent | 10
A5280 | Not Started | TWR.FINISHES.LEVEL04 | False Ceiling - Level 04 | Task Dependent | 10
A5290 | Not Started | TWR.FINISHES.LEVEL04 | Floor & Wall Tiling - Level 04 | Task Dependent | 10
A5300 | Not Started | TWR.FINISHES.LEVEL04 | Painting - Level 04 | Task Dependent | 10
A5310 | Not Started | TWR.FINISHES.LEVEL04 | Doors & Ironmongery - Level 04 | Task Dependent | 10
A5320 | Not Started | TWR.FINISHES.LEVEL04 | Kitchen & Wardrobe Joinery - Level 04 | Task Dependent | 10
A5330 | Not Started | TWR.FINISHES.LEVEL04 | MEP Second Fix & Fixtures - Level 04 | Task Dependent | 10
A5340 | Not Started | TWR.FINISHES.LEVEL04 | Final Cleaning & Snagging - Level 04 | Task Dependent | 10
A5350 | Not Started | TWR.FINISHES.LEVEL05 | Blockwork - Level 05 | Task Dependent | 10
A5360 | Not Started | TWR.FINISHES.LEVEL05 | Electrical First Fix - Level 05 | Task Dependent | 10
A5370 | Not Started | TWR.FINISHES.LEVEL05 | Plumbing First Fix - Level 05 | Task Dependent | 10
A5380 | Not Started | TWR.FINISHES.LEVEL05 | HVAC Ductwork & FCU Installation - Level 05 | Task Dependent | 10
A5390 | Not Started | TWR.FINISHES.LEVEL05 | Fire Fighting Sprinkler Piping - Level 05 | Task Dependent | 10
A5400 | Not Started | TWR.FINISHES.LEVEL05 | Fire Alarm & ELV Containment - Level 05 | Task Dependent | 10
A5410 | Not Started | TWR.FINISHES.LEVEL05 | Internal Plaster - Level 05 | Task Dependent | 10
A5420 | Not Started | TWR.FINISHES.LEVEL05 | Floor Screed - Level 05 | Task Dependent | 10
A5430 | Not Started | TWR.FINISHES.LEVEL05 | Wet Area Waterproofing - Level 05 | Task Dependent | 10
A5440 | Not Started | TWR.FINISHES.LEVEL05 | False Ceiling - Level 05 | Task Dependent | 10
A5450 | Not Started | TWR.FINISHES.LEVEL05 | Floor & Wall Tiling - Level 05 | Task Dependent | 10
A5460 | Not Started | TWR.FINISHES.LEVEL05 | Painting - Level 05 | Task Dependent | 10
A5470 | Not Started | TWR.FINISHES.LEVEL05 | Doors & Ironmongery - Level 05 | Task Dependent | 10
A5480 | Not Started | TWR.FINISHES.LEVEL05 | Kitchen & Wardrobe Joinery - Level 05 | Task Dependent | 10
A5490 | Not Started | TWR.FINISHES.LEVEL05 | MEP Second Fix & Fixtures - Level 05 | Task Dependent | 10
A5500 | Not Started | TWR.FINISHES.LEVEL05 | Final Cleaning & Snagging - Level 05 | Task Dependent | 10
A5510 | Not Started | TWR.FINISHES.LEVEL06 | Blockwork - Level 06 | Task Dependent | 10
A5520 | Not Started | TWR.FINISHES.LEVEL06 | Electrical First Fix - Level 06 | Task Dependent | 10
A5530 | Not Started | TWR.FINISHES.LEVEL06 | Plumbing First Fix - Level 06 | Task Dependent | 10
A5540 | Not Started | TWR.FINISHES.LEVEL06 | HVAC Ductwork & FCU Installation - Level 06 | Task Dependent | 10
A5550 | Not Started | TWR.FINISHES.LEVEL06 | Fire Fighting Sprinkler Piping - Level 06 | Task Dependent | 10
A5560 | Not Started | TWR.FINISHES.LEVEL06 | Fire Alarm & ELV Containment - Level 06 | Task Dependent | 10
A5570 | Not Started | TWR.FINISHES.LEVEL06 | Internal Plaster - Level 06 | Task Dependent | 10
A5580 | Not Started | TWR.FINISHES.LEVEL06 | Floor Screed - Level 06 | Task Dependent | 10
A5590 | Not Started | TWR.FINISHES.LEVEL06 | Wet Area Waterproofing - Level 06 | Task Dependent | 10
A5600 | Not Started | TWR.FINISHES.LEVEL06 | False Ceiling - Level 06 | Task Dependent | 10
A5610 | Not Started | TWR.FINISHES.LEVEL06 | Floor & Wall Tiling - Level 06 | Task Dependent | 10
A5620 | Not Started | TWR.FINISHES.LEVEL06 | Painting - Level 06 | Task Dependent | 10
A5630 | Not Started | TWR.FINISHES.LEVEL06 | Doors & Ironmongery - Level 06 | Task Dependent | 10
A5640 | Not Started | TWR.FINISHES.LEVEL06 | Kitchen & Wardrobe Joinery - Level 06 | Task Dependent | 10
A5650 | Not Started | TWR.FINISHES.LEVEL06 | MEP Second Fix & Fixtures - Level 06 | Task Dependent | 10
A5660 | Not Started | TWR.FINISHES.LEVEL06 | Final Cleaning & Snagging - Level 06 | Task Dependent | 10
A5670 | Not Started | TWR.FINISHES.LEVEL07 | Blockwork - Level 07 | Task Dependent | 10
A5680 | Not Started | TWR.FINISHES.LEVEL07 | Electrical First Fix - Level 07 | Task Dependent | 10
A5690 | Not Started | TWR.FINISHES.LEVEL07 | Plumbing First Fix - Level 07 | Task Dependent | 10
A5700 | Not Started | TWR.FINISHES.LEVEL07 | HVAC Ductwork & FCU Installation - Level 07 | Task Dependent | 10
A5710 | Not Started | TWR.FINISHES.LEVEL07 | Fire Fighting Sprinkler Piping - Level 07 | Task Dependent | 10
A5720 | Not Started | TWR.FINISHES.LEVEL07 | Fire Alarm & ELV Containment - Level 07 | Task Dependent | 10
A5730 | Not Started | TWR.FINISHES.LEVEL07 | Internal Plaster - Level 07 | Task Dependent | 10
A5740 | Not Started | TWR.FINISHES.LEVEL07 | Floor Screed - Level 07 | Task Dependent | 10
A5750 | Not Started | TWR.FINISHES.LEVEL07 | Wet Area Waterproofing - Level 07 | Task Dependent | 10
A5760 | Not Started | TWR.FINISHES.LEVEL07 | False Ceiling - Level 07 | Task Dependent | 10
A5770 | Not Started | TWR.FINISHES.LEVEL07 | Floor & Wall Tiling - Level 07 | Task Dependent | 10
A5780 | Not Started | TWR.FINISHES.LEVEL07 | Painting - Level 07 | Task Dependent | 10
A5790 | Not Started | TWR.FINISHES.LEVEL07 | Doors & Ironmongery - Level 07 | Task Dependent | 10
A5800 | Not Started | TWR.FINISHES.LEVEL07 | Kitchen & Wardrobe Joinery - Level 07 | Task Dependent | 10
A5810 | Not Started | TWR.FINISHES.LEVEL07 | MEP Second Fix & Fixtures - Level 07 | Task Dependent | 10
A5820 | Not Started | TWR.FINISHES.LEVEL07 | Final Cleaning & Snagging - Level 07 | Task Dependent | 10
A5830 | Not Started | TWR.FINISHES.LEVEL08 | Blockwork - Level 08 | Task Dependent | 10
A5840 | Not Started | TWR.FINISHES.LEVEL08 | Electrical First Fix - Level 08 | Task Dependent | 10
A5850 | Not Started | TWR.FINISHES.LEVEL08 | Plumbing First Fix - Level 08 | Task Dependent | 10
A5860 | Not Started | TWR.FINISHES.LEVEL08 | HVAC Ductwork & FCU Installation - Level 08 | Task Dependent | 10
A5870 | Not Started | TWR.FINISHES.LEVEL08 | Fire Fighting Sprinkler Piping - Level 08 | Task Dependent | 10
A5880 | Not Started | TWR.FINISHES.LEVEL08 | Fire Alarm & ELV Containment - Level 08 | Task Dependent | 10
A5890 | Not Started | TWR.FINISHES.LEVEL08 | Internal Plaster - Level 08 | Task Dependent | 10
A5900 | Not Started | TWR.FINISHES.LEVEL08 | Floor Screed - Level 08 | Task Dependent | 10
A5910 | Not Started | TWR.FINISHES.LEVEL08 | Wet Area Waterproofing - Level 08 | Task Dependent | 10
A5920 | Not Started | TWR.FINISHES.LEVEL08 | False Ceiling - Level 08 | Task Dependent | 10
A5930 | Not Started | TWR.FINISHES.LEVEL08 | Floor & Wall Tiling - Level 08 | Task Dependent | 10
A5940 | Not Started | TWR.FINISHES.LEVEL08 | Painting - Level 08 | Task Dependent | 10
A5950 | Not Started | TWR.FINISHES.LEVEL08 | Doors & Ironmongery - Level 08 | Task Dependent | 10
A5960 | Not Started | TWR.FINISHES.LEVEL08 | Kitchen & Wardrobe Joinery - Level 08 | Task Dependent | 10
A5970 | Not Started | TWR.FINISHES.LEVEL08 | MEP Second Fix & Fixtures - Level 08 | Task Dependent | 10
A5980 | Not Started | TWR.FINISHES.LEVEL08 | Final Cleaning & Snagging - Level 08 | Task Dependent | 10
A5990 | Not Started | TWR.FINISHES.LEVEL09 | Blockwork - Level 09 | Task Dependent | 10
A6000 | Not Started | TWR.FINISHES.LEVEL09 | Electrical First Fix - Level 09 | Task Dependent | 10
A6010 | Not Started | TWR.FINISHES.LEVEL09 | Plumbing First Fix - Level 09 | Task Dependent | 10
A6020 | Not Started | TWR.FINISHES.LEVEL09 | HVAC Ductwork & FCU Installation - Level 09 | Task Dependent | 10
A6030 | Not Started | TWR.FINISHES.LEVEL09 | Fire Fighting Sprinkler Piping - Level 09 | Task Dependent | 10
A6040 | Not Started | TWR.FINISHES.LEVEL09 | Fire Alarm & ELV Containment - Level 09 | Task Dependent | 10
A6050 | Not Started | TWR.FINISHES.LEVEL09 | Internal Plaster - Level 09 | Task Dependent | 10
A6060 | Not Started | TWR.FINISHES.LEVEL09 | Floor Screed - Level 09 | Task Dependent | 10
A6070 | Not Started | TWR.FINISHES.LEVEL09 | Wet Area Waterproofing - Level 09 | Task Dependent | 10
A6080 | Not Started | TWR.FINISHES.LEVEL09 | False Ceiling - Level 09 | Task Dependent | 10
A6090 | Not Started | TWR.FINISHES.LEVEL09 | Floor & Wall Tiling - Level 09 | Task Dependent | 10
A6100 | Not Started | TWR.FINISHES.LEVEL09 | Painting - Level 09 | Task Dependent | 10
A6110 | Not Started | TWR.FINISHES.LEVEL09 | Doors & Ironmongery - Level 09 | Task Dependent | 10
A6120 | Not Started | TWR.FINISHES.LEVEL09 | Kitchen & Wardrobe Joinery - Level 09 | Task Dependent | 10
A6130 | Not Started | TWR.FINISHES.LEVEL09 | MEP Second Fix & Fixtures - Level 09 | Task Dependent | 10
A6140 | Not Started | TWR.FINISHES.LEVEL09 | Final Cleaning & Snagging - Level 09 | Task Dependent | 10
A6150 | Not Started | TWR.FINISHES.LEVEL10 | Blockwork - Level 10 | Task Dependent | 10
A6160 | Not Started | TWR.FINISHES.LEVEL10 | Electrical First Fix - Level 10 | Task Dependent | 10
A6170 | Not Started | TWR.FINISHES.LEVEL10 | Plumbing First Fix - Level 10 | Task Dependent | 10
A6180 | Not Started | TWR.FINISHES.LEVEL10 | HVAC Ductwork & FCU Installation - Level 10 | Task Dependent | 10
A6190 | Not Started | TWR.FINISHES.LEVEL10 | Fire Fighting Sprinkler Piping - Level 10 | Task Dependent | 10
A6200 | Not Started | TWR.FINISHES.LEVEL10 | Fire Alarm & ELV Containment - Level 10 | Task Dependent | 10
A6210 | Not Started | TWR.FINISHES.LEVEL10 | Internal Plaster - Level 10 | Task Dependent | 10
A6220 | Not Started | TWR.FINISHES.LEVEL10 | Floor Screed - Level 10 | Task Dependent | 10
A6230 | Not Started | TWR.FINISHES.LEVEL10 | Wet Area Waterproofing - Level 10 | Task Dependent | 10
A6240 | Not Started | TWR.FINISHES.LEVEL10 | False Ceiling - Level 10 | Task Dependent | 10
A6250 | Not Started | TWR.FINISHES.LEVEL10 | Floor & Wall Tiling - Level 10 | Task Dependent | 10
A6260 | Not Started | TWR.FINISHES.LEVEL10 | Painting - Level 10 | Task Dependent | 10
A6270 | Not Started | TWR.FINISHES.LEVEL10 | Doors & Ironmongery - Level 10 | Task Dependent | 10
A6280 | Not Started | TWR.FINISHES.LEVEL10 | Kitchen & Wardrobe Joinery - Level 10 | Task Dependent | 10
A6290 | Not Started | TWR.FINISHES.LEVEL10 | MEP Second Fix & Fixtures - Level 10 | Task Dependent | 10
A6300 | Not Started | TWR.FINISHES.LEVEL10 | Final Cleaning & Snagging - Level 10 | Task Dependent | 10
A6310 | Not Started | TWR.FINISHES.LEVEL11 | Blockwork - Level 11 | Task Dependent | 10
A6320 | Not Started | TWR.FINISHES.LEVEL11 | Electrical First Fix - Level 11 | Task Dependent | 10
A6330 | Not Started | TWR.FINISHES.LEVEL11 | Plumbing First Fix - Level 11 | Task Dependent | 10
A6340 | Not Started | TWR.FINISHES.LEVEL11 | HVAC Ductwork & FCU Installation - Level 11 | Task Dependent | 10
A6350 | Not Started | TWR.FINISHES.LEVEL11 | Fire Fighting Sprinkler Piping - Level 11 | Task Dependent | 10
A6360 | Not Started | TWR.FINISHES.LEVEL11 | Fire Alarm & ELV Containment - Level 11 | Task Dependent | 10
A6370 | Not Started | TWR.FINISHES.LEVEL11 | Internal Plaster - Level 11 | Task Dependent | 10
A6380 | Not Started | TWR.FINISHES.LEVEL11 | Floor Screed - Level 11 | Task Dependent | 10
A6390 | Not Started | TWR.FINISHES.LEVEL11 | Wet Area Waterproofing - Level 11 | Task Dependent | 10
A6400 | Not Started | TWR.FINISHES.LEVEL11 | False Ceiling - Level 11 | Task Dependent | 10
A6410 | Not Started | TWR.FINISHES.LEVEL11 | Floor & Wall Tiling - Level 11 | Task Dependent | 10
A6420 | Not Started | TWR.FINISHES.LEVEL11 | Painting - Level 11 | Task Dependent | 10
A6430 | Not Started | TWR.FINISHES.LEVEL11 | Doors & Ironmongery - Level 11 | Task Dependent | 10
A6440 | Not Started | TWR.FINISHES.LEVEL11 | Kitchen & Wardrobe Joinery - Level 11 | Task Dependent | 10
A6450 | Not Started | TWR.FINISHES.LEVEL11 | MEP Second Fix & Fixtures - Level 11 | Task Dependent | 10
A6460 | Not Started | TWR.FINISHES.LEVEL11 | Final Cleaning & Snagging - Level 11 | Task Dependent | 10
A6470 | Not Started | TWR.FINISHES.LEVEL12 | Blockwork - Level 12 | Task Dependent | 10
A6480 | Not Started | TWR.FINISHES.LEVEL12 | Electrical First Fix - Level 12 | Task Dependent | 10
A6490 | Not Started | TWR.FINISHES.LEVEL12 | Plumbing First Fix - Level 12 | Task Dependent | 10
A6500 | Not Started | TWR.FINISHES.LEVEL12 | HVAC Ductwork & FCU Installation - Level 12 | Task Dependent | 10
A6510 | Not Started | TWR.FINISHES.LEVEL12 | Fire Fighting Sprinkler Piping - Level 12 | Task Dependent | 10
A6520 | Not Started | TWR.FINISHES.LEVEL12 | Fire Alarm & ELV Containment - Level 12 | Task Dependent | 10
A6530 | Not Started | TWR.FINISHES.LEVEL12 | Internal Plaster - Level 12 | Task Dependent | 10
A6540 | Not Started | TWR.FINISHES.LEVEL12 | Floor Screed - Level 12 | Task Dependent | 10
A6550 | Not Started | TWR.FINISHES.LEVEL12 | Wet Area Waterproofing - Level 12 | Task Dependent | 10
A6560 | Not Started | TWR.FINISHES.LEVEL12 | False Ceiling - Level 12 | Task Dependent | 10
A6570 | Not Started | TWR.FINISHES.LEVEL12 | Floor & Wall Tiling - Level 12 | Task Dependent | 10
A6580 | Not Started | TWR.FINISHES.LEVEL12 | Painting - Level 12 | Task Dependent | 10
A6590 | Not Started | TWR.FINISHES.LEVEL12 | Doors & Ironmongery - Level 12 | Task Dependent | 10
A6600 | Not Started | TWR.FINISHES.LEVEL12 | Kitchen & Wardrobe Joinery - Level 12 | Task Dependent | 10
A6610 | Not Started | TWR.FINISHES.LEVEL12 | MEP Second Fix & Fixtures - Level 12 | Task Dependent | 10
A6620 | Not Started | TWR.FINISHES.LEVEL12 | Final Cleaning & Snagging - Level 12 | Task Dependent | 10
A6630 | Not Started | TWR.FINISHES.LEVEL13 | Blockwork - Level 13 | Task Dependent | 10
A6640 | Not Started | TWR.FINISHES.LEVEL13 | Electrical First Fix - Level 13 | Task Dependent | 10
A6650 | Not Started | TWR.FINISHES.LEVEL13 | Plumbing First Fix - Level 13 | Task Dependent | 10
A6660 | Not Started | TWR.FINISHES.LEVEL13 | HVAC Ductwork & FCU Installation - Level 13 | Task Dependent | 10
A6670 | Not Started | TWR.FINISHES.LEVEL13 | Fire Fighting Sprinkler Piping - Level 13 | Task Dependent | 10
A6680 | Not Started | TWR.FINISHES.LEVEL13 | Fire Alarm & ELV Containment - Level 13 | Task Dependent | 10
A6690 | Not Started | TWR.FINISHES.LEVEL13 | Internal Plaster - Level 13 | Task Dependent | 10
A6700 | Not Started | TWR.FINISHES.LEVEL13 | Floor Screed - Level 13 | Task Dependent | 10
A6710 | Not Started | TWR.FINISHES.LEVEL13 | Wet Area Waterproofing - Level 13 | Task Dependent | 10
A6720 | Not Started | TWR.FINISHES.LEVEL13 | False Ceiling - Level 13 | Task Dependent | 10
A6730 | Not Started | TWR.FINISHES.LEVEL13 | Floor & Wall Tiling - Level 13 | Task Dependent | 10
A6740 | Not Started | TWR.FINISHES.LEVEL13 | Painting - Level 13 | Task Dependent | 10
A6750 | Not Started | TWR.FINISHES.LEVEL13 | Doors & Ironmongery - Level 13 | Task Dependent | 10
A6760 | Not Started | TWR.FINISHES.LEVEL13 | Kitchen & Wardrobe Joinery - Level 13 | Task Dependent | 10
A6770 | Not Started | TWR.FINISHES.LEVEL13 | MEP Second Fix & Fixtures - Level 13 | Task Dependent | 10
A6780 | Not Started | TWR.FINISHES.LEVEL13 | Final Cleaning & Snagging - Level 13 | Task Dependent | 10
A6790 | Not Started | TWR.FINISHES.LEVEL14 | Blockwork - Level 14 | Task Dependent | 10
A6800 | Not Started | TWR.FINISHES.LEVEL14 | Electrical First Fix - Level 14 | Task Dependent | 10
A6810 | Not Started | TWR.FINISHES.LEVEL14 | Plumbing First Fix - Level 14 | Task Dependent | 10
A6820 | Not Started | TWR.FINISHES.LEVEL14 | HVAC Ductwork & FCU Installation - Level 14 | Task Dependent | 10
A6830 | Not Started | TWR.FINISHES.LEVEL14 | Fire Fighting Sprinkler Piping - Level 14 | Task Dependent | 10
A6840 | Not Started | TWR.FINISHES.LEVEL14 | Fire Alarm & ELV Containment - Level 14 | Task Dependent | 10
A6850 | Not Started | TWR.FINISHES.LEVEL14 | Internal Plaster - Level 14 | Task Dependent | 10
A6860 | Not Started | TWR.FINISHES.LEVEL14 | Floor Screed - Level 14 | Task Dependent | 10
A6870 | Not Started | TWR.FINISHES.LEVEL14 | Wet Area Waterproofing - Level 14 | Task Dependent | 10
A6880 | Not Started | TWR.FINISHES.LEVEL14 | False Ceiling - Level 14 | Task Dependent | 10
A6890 | Not Started | TWR.FINISHES.LEVEL14 | Floor & Wall Tiling - Level 14 | Task Dependent | 10
A6900 | Not Started | TWR.FINISHES.LEVEL14 | Painting - Level 14 | Task Dependent | 10
A6910 | Not Started | TWR.FINISHES.LEVEL14 | Doors & Ironmongery - Level 14 | Task Dependent | 10
A6920 | Not Started | TWR.FINISHES.LEVEL14 | Kitchen & Wardrobe Joinery - Level 14 | Task Dependent | 10
A6930 | Not Started | TWR.FINISHES.LEVEL14 | MEP Second Fix & Fixtures - Level 14 | Task Dependent | 10
A6940 | Not Started | TWR.FINISHES.LEVEL14 | Final Cleaning & Snagging - Level 14 | Task Dependent | 10
A6950 | Not Started | TWR.FINISHES.LEVEL15 | Blockwork - Level 15 | Task Dependent | 10
A6960 | Not Started | TWR.FINISHES.LEVEL15 | Electrical First Fix - Level 15 | Task Dependent | 10
A6970 | Not Started | TWR.FINISHES.LEVEL15 | Plumbing First Fix - Level 15 | Task Dependent | 10
A6980 | Not Started | TWR.FINISHES.LEVEL15 | HVAC Ductwork & FCU Installation - Level 15 | Task Dependent | 10
A6990 | Not Started | TWR.FINISHES.LEVEL15 | Fire Fighting Sprinkler Piping - Level 15 | Task Dependent | 10
A7000 | Not Started | TWR.FINISHES.LEVEL15 | Fire Alarm & ELV Containment - Level 15 | Task Dependent | 10
A7010 | Not Started | TWR.FINISHES.LEVEL15 | Internal Plaster - Level 15 | Task Dependent | 10
A7020 | Not Started | TWR.FINISHES.LEVEL15 | Floor Screed - Level 15 | Task Dependent | 10
A7030 | Not Started | TWR.FINISHES.LEVEL15 | Wet Area Waterproofing - Level 15 | Task Dependent | 10
A7040 | Not Started | TWR.FINISHES.LEVEL15 | False Ceiling - Level 15 | Task Dependent | 10
A7050 | Not Started | TWR.FINISHES.LEVEL15 | Floor & Wall Tiling - Level 15 | Task Dependent | 10
A7060 | Not Started | TWR.FINISHES.LEVEL15 | Painting - Level 15 | Task Dependent | 10
A7070 | Not Started | TWR.FINISHES.LEVEL15 | Doors & Ironmongery - Level 15 | Task Dependent | 10
A7080 | Not Started | TWR.FINISHES.LEVEL15 | Kitchen & Wardrobe Joinery - Level 15 | Task Dependent | 10
A7090 | Not Started | TWR.FINISHES.LEVEL15 | MEP Second Fix & Fixtures - Level 15 | Task Dependent | 10
A7100 | Not Started | TWR.FINISHES.LEVEL15 | Final Cleaning & Snagging - Level 15 | Task Dependent | 10
A7110 | Not Started | TWR.FINISHES.LEVEL16 | Blockwork - Level 16 | Task Dependent | 10
A7120 | Not Started | TWR.FINISHES.LEVEL16 | Electrical First Fix - Level 16 | Task Dependent | 10
A7130 | Not Started | TWR.FINISHES.LEVEL16 | Plumbing First Fix - Level 16 | Task Dependent | 10
A7140 | Not Started | TWR.FINISHES.LEVEL16 | HVAC Ductwork & FCU Installation - Level 16 | Task Dependent | 10
A7150 | Not Started | TWR.FINISHES.LEVEL16 | Fire Fighting Sprinkler Piping - Level 16 | Task Dependent | 10
A7160 | Not Started | TWR.FINISHES.LEVEL16 | Fire Alarm & ELV Containment - Level 16 | Task Dependent | 10
A7170 | Not Started | TWR.FINISHES.LEVEL16 | Internal Plaster - Level 16 | Task Dependent | 10
A7180 | Not Started | TWR.FINISHES.LEVEL16 | Floor Screed - Level 16 | Task Dependent | 10
A7190 | Not Started | TWR.FINISHES.LEVEL16 | Wet Area Waterproofing - Level 16 | Task Dependent | 10
A7200 | Not Started | TWR.FINISHES.LEVEL16 | False Ceiling - Level 16 | Task Dependent | 10
A7210 | Not Started | TWR.FINISHES.LEVEL16 | Floor & Wall Tiling - Level 16 | Task Dependent | 10
A7220 | Not Started | TWR.FINISHES.LEVEL16 | Painting - Level 16 | Task Dependent | 10
A7230 | Not Started | TWR.FINISHES.LEVEL16 | Doors & Ironmongery - Level 16 | Task Dependent | 10
A7240 | Not Started | TWR.FINISHES.LEVEL16 | Kitchen & Wardrobe Joinery - Level 16 | Task Dependent | 10
A7250 | Not Started | TWR.FINISHES.LEVEL16 | MEP Second Fix & Fixtures - Level 16 | Task Dependent | 10
A7260 | Not Started | TWR.FINISHES.LEVEL16 | Final Cleaning & Snagging - Level 16 | Task Dependent | 10
A7270 | Not Started | TWR.FINISHES.LEVEL17 | Blockwork - Level 17 | Task Dependent | 10
A7280 | Not Started | TWR.FINISHES.LEVEL17 | Electrical First Fix - Level 17 | Task Dependent | 10
A7290 | Not Started | TWR.FINISHES.LEVEL17 | Plumbing First Fix - Level 17 | Task Dependent | 10
A7300 | Not Started | TWR.FINISHES.LEVEL17 | HVAC Ductwork & FCU Installation - Level 17 | Task Dependent | 10
A7310 | Not Started | TWR.FINISHES.LEVEL17 | Fire Fighting Sprinkler Piping - Level 17 | Task Dependent | 10
A7320 | Not Started | TWR.FINISHES.LEVEL17 | Fire Alarm & ELV Containment - Level 17 | Task Dependent | 10
A7330 | Not Started | TWR.FINISHES.LEVEL17 | Internal Plaster - Level 17 | Task Dependent | 10
A7340 | Not Started | TWR.FINISHES.LEVEL17 | Floor Screed - Level 17 | Task Dependent | 10
A7350 | Not Started | TWR.FINISHES.LEVEL17 | Wet Area Waterproofing - Level 17 | Task Dependent | 10
A7360 | Not Started | TWR.FINISHES.LEVEL17 | False Ceiling - Level 17 | Task Dependent | 10
A7370 | Not Started | TWR.FINISHES.LEVEL17 | Floor & Wall Tiling - Level 17 | Task Dependent | 10
A7380 | Not Started | TWR.FINISHES.LEVEL17 | Painting - Level 17 | Task Dependent | 10
A7390 | Not Started | TWR.FINISHES.LEVEL17 | Doors & Ironmongery - Level 17 | Task Dependent | 10
A7400 | Not Started | TWR.FINISHES.LEVEL17 | Kitchen & Wardrobe Joinery - Level 17 | Task Dependent | 10
A7410 | Not Started | TWR.FINISHES.LEVEL17 | MEP Second Fix & Fixtures - Level 17 | Task Dependent | 10
A7420 | Not Started | TWR.FINISHES.LEVEL17 | Final Cleaning & Snagging - Level 17 | Task Dependent | 10
A7430 | Not Started | TWR.FINISHES.BASEMENT2 | Basement Blockwork - B2 | Task Dependent | 10
A7440 | Not Started | TWR.FINISHES.BASEMENT2 | Basement MEP Services - B2 | Task Dependent | 10
A7450 | Not Started | TWR.FINISHES.BASEMENT2 | Epoxy Floor Coating - B2 | Task Dependent | 10
A7460 | Not Started | TWR.FINISHES.BASEMENT2 | Basement Painting - B2 | Task Dependent | 10
A7470 | Not Started | TWR.FINISHES.BASEMENT1 | Basement Blockwork - B1 | Task Dependent | 10
A7480 | Not Started | TWR.FINISHES.BASEMENT1 | Basement MEP Services - B1 | Task Dependent | 10
A7490 | Not Started | TWR.FINISHES.BASEMENT1 | Epoxy Floor Coating - B1 | Task Dependent | 10
A7500 | Not Started | TWR.FINISHES.BASEMENT1 | Basement Painting - B1 | Task Dependent | 10
A7510 | Not Started | TWR.FACADE | Curtain Wall Installation - Ground Floor | Task Dependent | 7.5
A7520 | Not Started | TWR.FACADE | Curtain Wall Installation - Level 01 | Task Dependent | 7.5
A7530 | Not Started | TWR.FACADE | Curtain Wall Installation - Level 02 | Task Dependent | 7.5
A7540 | Not Started | TWR.FACADE | Curtain Wall Installation - Level 03 | Task Dependent | 7.5
A7550 | Not Started | TWR.FACADE | Curtain Wall Installation - Level 04 | Task Dependent | 7.5
A7560 | Not Started | TWR.FACADE | Curtain Wall Installation - Level 05 | Task Dependent | 7.5
A7570 | Not Started | TWR.FACADE | Curtain Wall Installation - Level 06 | Task Dependent | 7.5
A7580 | Not Started | TWR.FACADE | Curtain Wall Installation - Level 07 | Task Dependent | 7.5
A7590 | Not Started | TWR.FACADE | Curtain Wall Installation - Level 08 | Task Dependent | 7.5
A7600 | Not Started | TWR.FACADE | Curtain Wall Installation - Level 09 | Task Dependent | 7.5
A7610 | Not Started | TWR.FACADE | Curtain Wall Installation - Level 10 | Task Dependent | 7.5
A7620 | Not Started | TWR.FACADE | Curtain Wall Installation - Level 11 | Task Dependent | 7.5
A7630 | Not Started | TWR.FACADE | Curtain Wall Installation - Level 12 | Task Dependent | 7.5
A7640 | Not Started | TWR.FACADE | Curtain Wall Installation - Level 13 | Task Dependent | 7.5
A7650 | Not Started | TWR.FACADE | Curtain Wall Installation - Level 14 | Task Dependent | 7.5
A7660 | Not Started | TWR.FACADE | Curtain Wall Installation - Level 15 | Task Dependent | 7.5
A7670 | Not Started | TWR.FACADE | Curtain Wall Installation - Level 16 | Task Dependent | 7.5
A7680 | Not Started | TWR.FACADE | Curtain Wall Installation - Level 17 | Task Dependent | 7.5
A7690 | Not Started | TWR.ROOF | Roof Waterproofing & Insulation | Task Dependent | 10
A7700 | Not Started | TWR.ROOF | Roof Screed & Tiling | Task Dependent | 7.5
A7710 | Not Started | TWR.ROOF | Rooftop MEP Plant Installation | Task Dependent | 25
A7720 | Not Started | TWR.VERTICALT | Lift Installation - Lift 1 | Task Dependent | 50
A7730 | Not Started | TWR.VERTICALT | Lift Installation - Lift 2 | Task Dependent | 50
A7740 | Not Started | TWR.VERTICALT | Lift Installation - Lift 3 | Task Dependent | 50
A7750 | Not Started | TWR.VERTICALT | Lift Installation - Lift 4 | Task Dependent | 50
A7760 | Not Started | TWR.COMMISSION | Testing & Commissioning - MEP Systems | Task Dependent | 50
A7770 | Not Started | TWR.EXTERNALW | External Works - Hardscape & Roads | Task Dependent | 37.5
A7780 | Not Started | TWR.EXTERNALW | External Works - Landscaping | Task Dependent | 25
A7790 | Not Started | TWR.EXTERNALW | Boundary Wall & Gates | Task Dependent | 18.75